## Change History
Sl. No. | Reported by | Issue | Status | Type | Analysis | Implementation Status | Designer Level Testing Status | ChangeId for traceability | DB Change
1 | Recruitment | When PWD selected, Scribe requirement to be captured as Yes/No | Closed | Requirement |  | Done | Tested | 2023110703
| Recruitment | When Scribe Required is set to Yes, and then PWD changed back to NO, Scribe Required not getting reset. | Closed | Observation |  | Done | Tested | 2025050701
| Recruitment | Help Desk phone number 4030 should be removed | Closed | Requirement |  | Done | Tested | 2025050702
| Recruitment | Ex-Serviceman Yes/No not shown in preview pdf | Closed | Observation |  | Done | Tested | 2025050703
| Recruitment | Age limit for MSc-Tech is to be changed from 30 to 28 | Closed | Requirement |  | Done | Tested | 2025050704
| Recruitment | Age limit validation shall be w.r.t end date of Advertisement | Closed | Requirement |  | Done | Tested | 2025050705
| Recruitment | "Educational Qualification" text shall be "Educational Qualifications" | Closed | Requirement |  | Done | Tested | 2025050706
| Recruitment | After the field 'Do you need a scribe' the following point may be inserted : “Do you need compensatory time”? (Disclaimer to be added after these two points – “Please go through the Point no 15 of advertisement” if opted Yes.) | Closed | Requirement |  | Done | Tested | 2025050903
| Recruitment | On registartion page, when password mismatch is reported and password is corrected by editing password field, instead of password_repeat field, error doesn’t go away | Closed | Observation |  | Done | Tested | 2025050707
| Recruitment | Mark Validation-Where a University mentions both CGPA and percentage of marks in its Degree Certificate or Consolidated Mark sheet, then at least one criteria (either CGPA or percentage) should meet the eligibility criteria. | Closed | Requirement |  | Done | Tested | 2025050708
| Recruitment | Certificate Preview option can be considered | Closed | Requirement |  | Done | Tested | 2025050709
| Recruitment | Instead of Point (e), (f), (g) in the Important Instruction window, the following point may be inserted: "A copy of Candidate's SC/ST/OBC/EWS/PwBD certificate/Ex-Servicemen discharge certificate." | Closed | Requirement |  | Done | Tested | 2025050801
| Recruitment | In point C of instructions page 'Mark Sheets' also to be added along with the certificate. | Closed | Requirement |  | Done | Tested | 2025050802
| Recruitment | While uploading, Special Characters (space) are not allowed in the file name. | Closed | Information | As per the best security practices |  |  | NA
| Recruitment | Selected preferences are not assured/ replaced with as per the below lines in the advertisement "Allotment of Examination City as opted by a candidate will be strictly subject to administrative exigencies. In case it is not feasible to accommodate any candidate in the opted City, he/she will be assigned the next feasible Examination city/ Hyderabad." | Closed | Requirement |  | Done | Tested | 2025050803
| Recruitment | Skill test should be removed in Experience details (Interview/written test should be put) | Closed | Requirement |  | Done | Tested | 2025050804
| Recruitment | A popup is coming for excess age limit candidate as “Based on your category” to be removed and replaced with “As your age is beyond Age limit" Age validation is on the late date of submission of application i.e. 30.05.2025 | Closed | Requirement |  | Done | Tested | 2025050805
| Recruitment | If University provides either CGPA or percentage enter either of it ( disclaimer message if this option is unable to be displayed in meanwhile time. ) Where a University mentions both CGPA and percentage of marks in its Degree Certificate or Consolidated Mark sheet, then at least one criteria (either CGPA or percentage) should meet the eligibility criteria. | Closed | Requirement |  | Done | Tested | 2025050806
| Recruitment | Exservice => Ex-serviceman | Closed | Observation |  | Done | Tested | 2025050901
| Recruitment | Ex-Service certificate shall not be displayed in preview, When Ex-Serviceman is No | Closed | Observation |  | Done | Tested | 2025050902
| Applicant | Bank Beneficiary Error while Submitting | Closed | Observation |  | Done |  | 2025051301
| Development Team | DoubleVerification shall not updated application status if it is already PAID or POSTED | Closed | Observation |  | Done |  | 2025051302
| Development Team | UpdateDoubleVerification toUpperCase removed | Closed | Observation |  | Done |  | 2025051401
| Development Team | Dual Applications due to UNKNOWN Status in personal_data table | Closed | Observation |  | Done |  | 2025051402
| Applicant | Invalid Higher Educations details year validation | Closed | Observation |  | Done |  | 2025051501
| Development Team | S2S script between LOBA and NBPG updated | Closed | Observation |  | Done
| Development Team | Invalid status PAYMNTFAILED set in personal_data instead of PAYMENTFAILED And "Payment Initiated" was checked instead of "Payment initiated" | Closed | Observation |  | Done |  | 2025051601
| Development Team | Email Sending for Information | [5 empty] | 2025051602
| Development Team | PAYMNTFAILED is still persists. Instead this status is also included in the logic. | Closed | Observation |  | Done |  | 2025052001
| Recruitment | FAQ on recruitment Portal | Closed | Requirement |  | Done |  | 2025052002
| Recruitment | Name length needs to be increased to 60 | [5 empty] | 2025052003
| Recruitment | IIT Kharagpur to be added | Closed | Requirement |  | Done |  | NA